## Master Calendar
OAK'S LAB — H2 2026 Content Calendar
Owner = pillar owner (validates angle, primary interview source). Byline = published name. Drafted by = first-draft writer (Nur for all long-form).
ID | Type | Title | Pillar | Owner | Byline | Drafted by | Reviewers / input | Target month | Stage | Status | Source | Notes
INDUSTRY REPORTS (3) — gated PDFs, distribution tentpoles
R1 | Industry report | AI-Native Delivery: A 2026 Playbook for Engineering Leaders | AI-Native Delivery | Andy | OAK'S LAB (Theo intro byline) | Nur (via interviews with Andy + Krystof + rotating DMT) | Andy (pillar validation), Jake (framing), Krystof + rotating DMT senior eng (technical interviews), Theo (intro byline), Ha (design), Barbora (coord) | Aug 2026 | Convert | Committed | — | Launch week 2. Kickoff mid-June. Renamed from 'AI in Production' — title now signals AI-as-delivery-practice (not AI-as-product-feature). Pairs with W6.
R2 | Industry report | Engineering in Healthcare: A Practitioner's Playbook for 2026 (working title) | Deep Domain Expertise | DMT (rotating) | OAK'S LAB | Nur (via interviews with DMT healthcare leads) | DMT healthcare leads (pillar validation + technical interviews + review), Josh (partnership angle), Ha (design), Barbora (coord) | Oct 2026 | Convert | Committed | — | Launch week 3. Kickoff mid-August. OpenLoop named-client permission anchors the report.
R3 | Industry report | What CTOs Are Building in 2027: A Tech Stack Survey | AI-Native Delivery | Andy | OAK'S LAB (Jake foreword + Andy validation) | Nur (via survey analysis + Andy interviews) | Andy (pillar validation + survey design), Jake (foreword byline + POV), Sean (outbound survey distribution), DMT (technical interpretation), Ha (design), Barbora (coord) | Late Nov 2026 | Convert | Committed | — | Replaces 'State of Engineering in Finance 2026' — Jake's call. Forward-looking AI tech-stack survey, 50+ CTO responses. T11 is the launch companion.
GATED DOWNLOADABLES (4) — Convert-stage sales tools
D1 | Gated downloadable | SaaS Scaling Guide v4 | Elite Engineering Talent | Kuba (pending) | OAK'S LAB | Nur | Kuba (pillar validation, pending Andy confirm), Jake (approval done), Ha (design in progress) | Jun 2026 | Convert | In design | — | Launching this week as LinkedIn Lead Gen play.
D2 | Gated downloadable | Choosing a Dev Partner: A CTO's Buyer's Guide | Outsourcing | Jake | OAK'S LAB | Nur | Jake (pillar validation + framing), Barbora (coord), Ha (design) | Q3–Q4 2026 | Convert | Idea | — | ~60% repurpose. T1 is the public-access summary.
D3 | Gated downloadable | The Roadmap Reality Check: A CPO's Field Guide | Product Thinking | Denisa | Matej Novak | Nur (via interviews with Matej + Denisa) | Denisa (pillar validation), Matej (interview + review + byline), Ha (design) | Q3–Q4 2026 | Convert | Idea | — | First CPO-targeted downloadable.
D4 | Gated downloadable | The AI-Native Engineering Team: A CTO's Operating Playbook | AI-Native Delivery | Andy | OAK'S LAB | Nur (via interviews with Andy + Krystof) | Andy (pillar validation), Krystof + DMT (technical interviews), Jake (framing), Ha (design) | Q4 2026 | Convert | Idea | — | Replaces '20-to-200 Engineering Scaling Playbook'. Closes Convert-stage gap on AI-Native Delivery.
TL ARTICLES (12) — fresh long-form, June through December
T1 | TL article | Choosing Your Outsourcing Partner: A CTO's Decision Framework | Outsourcing | Jake | Jake | Nur | Jake (pillar owner + byline), Sean (amplifier) | Jun 2026 | Create + Capture | Committed | — | Replaces 'Four-Year Partnership Pattern'. Year-opener for Outsourcing. Drives D2 downloads.
T2 | TL article | Why "More Engineers" Is Almost Never the Answer | Product Thinking | Denisa | Jake | Nur | Denisa (pillar validation), Josh (amplifier) | Jun 2026 | Create + Capture | Committed | — | Counter-argues headcount-first thinking.
T3 | TL article | Inside the OAK'S LAB Way: How Senior Engineers Ramp in Week One | Elite Engineering Talent | Kuba (pending) | Jan Barta | Nur (via interview with Jan) | Kuba (pillar validation, pending Andy confirm), Jan (review + byline), Tonda (delivery process input) | Jul 2026 | Create + Capture | Committed | — | First Elite Eng Talent piece.
T4 | TL article | Production AI Patterns: RAG (Series 1 of 2) | AI-Native Delivery | Andy | DMT (Krystof or rotating) | Nur (via interview with Krystof / DMT) | Andy (pillar validation), Krystof or rotating DMT senior eng (review + byline) | Jul 2026 | Create + Capture | Committed | — | Pre-warms R1 audience.
T5 | TL article | Why CTOs Get the AI Question Wrong | AI-Native Delivery | Andy | Jake | Nur | Andy (pillar validation), Jake (review + byline) | Aug 2026 | Create + Capture | Committed | R1 | R1 launch companion. CTO-targeted (was 'Founders' — demoted).
T6 | TL article | The Product Roadmap Test: 5 Questions Every CPO Should Ask Before Approving Next Sprint | Product Thinking | Denisa | Matej Novak | Nur (via interview with Matej) | Denisa (pillar validation), Matej (interview + review + byline) | Aug 2026 | Create + Capture | Committed | — | 5-question framework + forced-ranking. Pairs with D3.
T7 | TL article | Production AI Patterns: Eval Loops (Series 2 of 2) | AI-Native Delivery | Andy | DMT (Krystof) | Nur (via interview with Krystof / DMT) | Andy (pillar validation), Krystof or rotating DMT (review + byline), Jake (amplifier) | Sep 2026 | Create + Capture | Committed | — | Sustains AI authority post-R1 launch.
T8 | TL article | The Real Cost of a 12-Month Engineering Push: Hire vs Partner | Outsourcing | Jake | Theo | Nur (via interview with Theo) | Jake (pillar owner + framing), Theo (review + byline), Jake (amplifier) | Sep 2026 | Create + Capture | Committed | — | Theo's first major piece. Closes the case T1 opens.
T9 | TL article | AI Code Review: What's Actually Working in Production | Elite Engineering Talent | Kuba (pending) | DMT (Krystof) | Nur (via interview with Krystof) | Kuba (pillar validation, pending Andy confirm), Krystof (review + byline) | Oct 2026 | Create + Capture | Committed | — | Cross-threads AI-Native and Elite Eng Talent.
T10 | TL article | Compliance-by-Design: Avoiding the Late-Stage Rewrite | Deep Domain Expertise | DMT (rotating) | Jake | Nur | DMT healthcare lead (pillar validation), Jake (review + byline), DMT (technical review) | Oct 2026 | Create + Capture | Committed | R2 | R2 launch companion. Drives Healthcare report downloads.
T11 | TL article | Inside Our AI Delivery Process: How an AI-Native Team Actually Ships | AI-Native Delivery | Andy | Andy | Nur (via interview with Andy + Krystof) | Andy (pillar owner + byline), Krystof + DMT (process detail interviews), Jake (review) | Nov 2026 | Create + Capture | Committed | R3 | Replaces 'Pair Product and Engineering'. R3 launch companion. Pairs with W6.
T12 | TL article | Compliance Across Verticals: A CTO's Operating Framework | Elite Engineering Talent | Kuba (pending) | Jake | Nur | Kuba (pillar validation, pending Andy confirm), Jake (review + byline), DMT (cross-vertical input) | Dec 2026 | Create + Capture | Committed | — | Replaces 'Why Founders Get the Compliance Conversation Wrong'. Cross-vertical operating framework.
CASE STUDIES (5) — long-form client proof
C1 | Case study | Swiftly | Elite Engineering Talent | Kuba (pending) | Josh | Josh + Nur | Kuba (pillar validation, pending Andy confirm), Ha (design) | TBD 2026 | Convert | In production | — | General permission in place.
C2 | Case study | OpenLoop Health (or anonymized) | Deep Domain Expertise | DMT (rotating) | Josh | Josh + Nur | DMT healthcare lead (pillar validation), Ha (design), Andy (approval) | Jun 2026 | Convert | In Webflow | — | Text live in Webflow draft. Image upload + Jake sign-off pending.
C3 | Case study | Nasdaq Private Market (or anonymized) | Deep Domain Expertise | DMT (rotating) | Josh | Josh + Nur | DMT finance lead (pillar validation), Ha (design), Andy (approval) | TBD 2026 | Convert | Permissions pending | — | Named permissions uncertain.
C4 | Case study | Exam Papers Plus | Deep Domain Expertise | DMT (rotating) | Josh | Josh + Nur | DMT education lead (pillar validation), Ha (design), Andy (approval) | Q3 2026 | Convert | To start | — | New edtech client. Anchors W1.
C5 | Case study | Learning Spring | Deep Domain Expertise | DMT (rotating) | Josh | Josh + Nur | DMT education lead (pillar validation), Ha (design), Andy (approval) | Q3 2026 | Convert | To start | — | New edtech client. Second proof point for W1.
WEB PAGES (13) — industry, services, situations
W1 | Industry page | Education industry page (new) | Deep Domain Expertise | DMT (rotating) | OAK'S LAB | Nur | DMT education lead (pillar validation), Barbora (coord), Ha (design), Lukas (build), Josh (case study input) | Q3 2026 | Capture | To start | — | Top priority. Anchored by C4 + C5.
W2 | Industry page | Finance industry page (rename from Fintech) | Deep Domain Expertise | DMT (rotating) | OAK'S LAB | Nur (copy refresh) | DMT finance lead (pillar validation), Barbora (coord), Ha (design), Lukas (build) | Q3 2026 | Capture | In flight | — | Lukas brief shipped.
W3 | Industry page | Healthcare industry page (rename from Healthtech) | Deep Domain Expertise | DMT (rotating) | OAK'S LAB | Nur (copy refresh) | DMT healthcare lead (pillar validation), Barbora (coord), Ha (design), Lukas (build) | Q3 2026 | Capture | In flight | — | Rename + content update.
W4 | Industry page | Cybersecurity industry page | Deep Domain Expertise | DMT (rotating) | OAK'S LAB | Nur (light refresh) | DMT cybersec lead (pillar validation), Ha (design), Lukas (build) | Q3–Q4 2026 | Capture | To start | — | Light refresh.
W5 | Industry page | SaaS industry page | Product Thinking + Elite Engineering Talent | Denisa + Kuba (pending) | OAK'S LAB | Nur (light refresh) | Denisa + Kuba (pillar validation, pending Andy confirm on Kuba), Ha (design), Lukas (build) | Q3–Q4 2026 | Capture | To start | — | Track 2 audience.
W6 | Services page | AI Native Development (new) | AI-Native Delivery | Andy | OAK'S LAB | Nur | Andy (pillar validation), Krystof (input), Jake (review), Ha (design), Lukas (build) | Aug 2026 | Capture | To start | — | Replaces old Software Development page. Anchored by D4 + T11.
W7 | Services page | Design & Discovery (refresh) | Product Thinking | Denisa | OAK'S LAB | Nur (light refresh) | Denisa (pillar validation + input), Ha (design), Lukas (build) | Q3–Q4 2026 | Capture | To start | — | Renamed from Product Discovery & Design.
W8 | Services page | Agentic AI Systems (refresh) | AI-Native Delivery | Andy | OAK'S LAB | Nur (light refresh) | Andy (pillar validation), Krystof (input), Ha (design), Lukas (build) | Q3–Q4 2026 | Capture | To start | — | AI as product feature (clients build) — distinct from W6.
W9 | Situations page (SEO) | Launching a new product | Outsourcing | Jake | OAK'S LAB | Nur | Jake (pillar owner), Ha (design), Lukas (build) | Q4 2026 / Q1 2027 | Capture | To start | — | SEO: 'launching new product team.'
W10 | Situations page (SEO) | Scaling an existing product | Elite Engineering Talent | Kuba (pending) | OAK'S LAB | Nur | Kuba (pillar validation, pending Andy confirm), Ha (design), Lukas (build) | Q4 2026 / Q1 2027 | Capture | To start | — | SEO: 'scaling engineering team.'
W11 | Situations page (SEO) | Integrating AI into your product | AI-Native Delivery | Andy | OAK'S LAB | Nur | Andy (pillar validation), Ha (design), Lukas (build) | Q4 2026 / Q1 2027 | Capture | To start | — | SEO: 'AI integration in product.'
W12 | Situations page (SEO) | Strengthening your product org | Product Thinking | Denisa | OAK'S LAB | Nur | Denisa (pillar validation), Ha (design), Lukas (build) | Q4 2026 / Q1 2027 | Capture | To start | — | SEO: 'embedded product team.'
W13 | Situations page (SEO) | Establishing your European engineering hub | Outsourcing | Jake | OAK'S LAB | Nur | Jake (pillar owner), Ha (design), Lukas (build) | Q4 2026 / Q1 2027 | Capture | To start | — | SEO: 'European engineering hub.'
KNOWLEDGE HUB BACKLOG (120 articles, batched monthly)
K1 | KH backlog | June batch (20/120 cumulative) | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — review only | Nur (review), Ha (hero pass), Barbora (QA) | Jun 2026 | Awareness + Capture | Committed | — | Light TOV edit + SEO check + upload.
K2 | KH backlog | July batch (40/120 cumulative) | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — review only | Nur (review), Ha (hero pass), Barbora (QA) | Jul 2026 | Awareness + Capture | Committed | —
K3 | KH backlog | August batch (60/120 cumulative) | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — review only | Nur (review), Ha (hero pass), Barbora (QA) | Aug 2026 | Awareness + Capture | Committed | —
K4 | KH backlog | September batch (80/120 cumulative) | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — review only | Nur (review), Ha (hero pass), Barbora (QA) | Sep 2026 | Awareness + Capture | Committed | —
K5 | KH backlog | October batch (100/120 cumulative) | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — review only | Nur (review), Ha (hero pass), Barbora (QA) | Oct 2026 | Awareness + Capture | Committed | — | Target: 120/120 indexed by end of October.
K6 | KH backlog | Nov–Dec maintenance | All 5 pillars | Barbora (coord) | OAK'S LAB | Existing — maintenance | Nur (maintenance), Barbora | Nov–Dec 2026 | Awareness + Capture | Committed | — | Internal linking, dead-link sweep.
NEWSLETTERS (3)
N1 | Newsletter | July newsletter (+ AI Roundup section) | — | Barbora | OAK'S LAB | — | — | Jul 2026 | Awareness | Committed | — | Email to ~3,000 subscribers. New AI Roundup section.
N2 | Newsletter | October newsletter (+ AI Roundup section) | — | Barbora | OAK'S LAB | — | — | Oct 2026 | Awareness | Committed | — | AI Roundup recurring.
N3 | Newsletter | December newsletter (year-end + AI Roundup) | — | Barbora | OAK'S LAB | — | — | Dec 2026 | Awareness | Committed | — | Year-end edition + AI Roundup.
EMAIL NURTURE FLOWS (2) — drip sequences triggered by downloadable submits
E1 | Email nurture flow | Flow A — Website downloads (5 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | Barbora | Barbora | Nur (review), HubSpot workflow build | Aug 2026 launch | Convert | To start | D1, D2, D3, D4, R1, R2, R3 | Triggered on any oakslab.com downloadable submit.
E2 | Email nurture flow | Flow B — LinkedIn Lead Gen (4 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | Barbora | Barbora | Nur (review), HubSpot workflow build | Sprint 11–12 (accelerated) | Convert | To start | Triggered by LinkedIn Lead Gen forms | Wave 2 Stage A is the trigger. Gentler than Flow A.
SHORT-FORM LINKEDIN POSTS (Jake monthly standalones + Theo H2 + team posts)
SF-Jun-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support on prompts/framing) | Jun 2026 | Awareness + Create | Planned | — | CTO challenges-style, founder voice, opportunistic topics — client moments, lessons, hot takes. Pairs with T1 + T2 launches.
SF-Jul-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Jul 2026 | Awareness + Create | Planned | — | Pairs with T3 (Jan Barta byline) and T4 (DMT byline) launches — Jake amplifies.
SF-Aug-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Aug 2026 | Awareness + Create | Planned | — | R1 launch month — expect concentrated bursts around R1 launch week alongside T5 (Jake) companion post.
SF-Sep-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Sep 2026 | Awareness + Create | Planned | — | Post-R1 momentum window. Pairs with T7 (DMT) and T8 (Theo) launches — Jake amplifies on his channel.
SF-Oct-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Oct 2026 | Awareness + Create | Planned | — | R2 launch month — expect bursts alongside T10 (Jake) companion post.
SF-Nov-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Nov 2026 | Awareness + Create | Planned | — | R3 launch month (late Nov). T11 is Andy byline — Jake amplifies + posts standalones alongside the R3 launch burst.
SF-Dec-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jake | Jake (self) | Barbora (light support) | Dec 2026 | Awareness + Create | Planned | — | Post-R3 momentum + year-end. Pairs with T12 (Jake) companion post.
SF-H2-T | Standalone short-form (Theo) | Theo occasional LinkedIn posts (~7–14 across H2) | Multiple | Jake / Theo | Theo | Theo (self) | Barbora (light support) | Jun–Dec 2026 | Awareness + Create | Planned | — | Posts when substantive, ~1–2/mo. Higher-credibility exec voice. Each one is a TLA candidate.
SF-Team | Team short-form | Team voices on individual cadences (Sean, Josh, Matej, others) | All 5 pillars | Barbora (coord) | Multiple | Voices on individual cadences | — | Jun–Dec 2026 | Awareness + Create | Planned | — | Sean (2-3/wk highest volume), Josh (1/wk), Matej (~weekly), Denisa/Andy occasional. Mostly opportunistic + companion posts to long-form launches.

## By Month
What ships when — month by month
Month | ID | Type | Title | Pillar | Owner | Status
Jun 2026
| D1 | Gated downloadable | SaaS Scaling Guide v4 | Elite Engineering Talent | Kuba (pending) | In design
| T1 | TL article | Choosing Your Outsourcing Partner: A CTO's Decision Framework | Outsourcing | Jake | Committed
| T2 | TL article | Why "More Engineers" Is Almost Never the Answer | Product Thinking | Denisa | Committed
| C2 | Case study | OpenLoop Health (or anonymized) | Deep Domain Expertise | DMT (rotating) | In Webflow
| K1 | KH backlog | June batch (20/120 cumulative) | All 5 pillars | Barbora (coord) | Committed
| SF-Jun-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Jul 2026
| T3 | TL article | Inside the OAK'S LAB Way: How Senior Engineers Ramp in Week One | Elite Engineering Talent | Kuba (pending) | Committed
| T4 | TL article | Production AI Patterns: RAG (Series 1 of 2) | AI-Native Delivery | Andy | Committed
| K2 | KH backlog | July batch (40/120 cumulative) | All 5 pillars | Barbora (coord) | Committed
| N1 | Newsletter | July newsletter (+ AI Roundup section) | — | Barbora | Committed
| SF-Jul-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Aug 2026
| R1 | Industry report | AI-Native Delivery: A 2026 Playbook for Engineering Leaders | AI-Native Delivery | Andy | Committed
| T5 | TL article | Why CTOs Get the AI Question Wrong | AI-Native Delivery | Andy | Committed
| T6 | TL article | The Product Roadmap Test: 5 Questions Every CPO Should Ask Before Approving Next Sprint | Product Thinking | Denisa | Committed
| W6 | Services page | AI Native Development (new) | AI-Native Delivery | Andy | To start
| K3 | KH backlog | August batch (60/120 cumulative) | All 5 pillars | Barbora (coord) | Committed
| SF-Aug-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Aug 2026 launch
| E1 | Email nurture flow | Flow A — Website downloads (5 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | To start
Sep 2026
| T7 | TL article | Production AI Patterns: Eval Loops (Series 2 of 2) | AI-Native Delivery | Andy | Committed
| T8 | TL article | The Real Cost of a 12-Month Engineering Push: Hire vs Partner | Outsourcing | Jake | Committed
| K4 | KH backlog | September batch (80/120 cumulative) | All 5 pillars | Barbora (coord) | Committed
| SF-Sep-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Oct 2026
| R2 | Industry report | Engineering in Healthcare: A Practitioner's Playbook for 2026 (working title) | Deep Domain Expertise | DMT (rotating) | Committed
| T9 | TL article | AI Code Review: What's Actually Working in Production | Elite Engineering Talent | Kuba (pending) | Committed
| T10 | TL article | Compliance-by-Design: Avoiding the Late-Stage Rewrite | Deep Domain Expertise | DMT (rotating) | Committed
| K5 | KH backlog | October batch (100/120 cumulative) | All 5 pillars | Barbora (coord) | Committed
| N2 | Newsletter | October newsletter (+ AI Roundup section) | — | Barbora | Committed
| SF-Oct-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Nov 2026
| T11 | TL article | Inside Our AI Delivery Process: How an AI-Native Team Actually Ships | AI-Native Delivery | Andy | Committed
| SF-Nov-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Late Nov 2026
| R3 | Industry report | What CTOs Are Building in 2027: A Tech Stack Survey | AI-Native Delivery | Andy | Committed
Dec 2026
| T12 | TL article | Compliance Across Verticals: A CTO's Operating Framework | Elite Engineering Talent | Kuba (pending) | Committed
| N3 | Newsletter | December newsletter (year-end + AI Roundup) | — | Barbora | Committed
| SF-Dec-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Planned
Nov–Dec 2026
| K6 | KH backlog | Nov–Dec maintenance | All 5 pillars | Barbora (coord) | Committed
Q3 2026
| C4 | Case study | Exam Papers Plus | Deep Domain Expertise | DMT (rotating) | To start
| C5 | Case study | Learning Spring | Deep Domain Expertise | DMT (rotating) | To start
| W1 | Industry page | Education industry page (new) | Deep Domain Expertise | DMT (rotating) | To start
| W2 | Industry page | Finance industry page (rename from Fintech) | Deep Domain Expertise | DMT (rotating) | In flight
| W3 | Industry page | Healthcare industry page (rename from Healthtech) | Deep Domain Expertise | DMT (rotating) | In flight
Q3–Q4 2026
| D2 | Gated downloadable | Choosing a Dev Partner: A CTO's Buyer's Guide | Outsourcing | Jake | Idea
| D3 | Gated downloadable | The Roadmap Reality Check: A CPO's Field Guide | Product Thinking | Denisa | Idea
| W4 | Industry page | Cybersecurity industry page | Deep Domain Expertise | DMT (rotating) | To start
| W5 | Industry page | SaaS industry page | Product Thinking + Elite Engineering Talent | Denisa + Kuba (pending) | To start
| W7 | Services page | Design & Discovery (refresh) | Product Thinking | Denisa | To start
| W8 | Services page | Agentic AI Systems (refresh) | AI-Native Delivery | Andy | To start
Q4 2026
| D4 | Gated downloadable | The AI-Native Engineering Team: A CTO's Operating Playbook | AI-Native Delivery | Andy | Idea
Sprint 11–12 (accelerated)
| E2 | Email nurture flow | Flow B — LinkedIn Lead Gen (4 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | To start
Q4 2026 / Q1 2027
| W9 | Situations page (SEO) | Launching a new product | Outsourcing | Jake | To start
| W10 | Situations page (SEO) | Scaling an existing product | Elite Engineering Talent | Kuba (pending) | To start
| W11 | Situations page (SEO) | Integrating AI into your product | AI-Native Delivery | Andy | To start
| W12 | Situations page (SEO) | Strengthening your product org | Product Thinking | Denisa | To start
| W13 | Situations page (SEO) | Establishing your European engineering hub | Outsourcing | Jake | To start
Jun–Dec 2026
| SF-H2-T | Standalone short-form (Theo) | Theo occasional LinkedIn posts (~7–14 across H2) | Multiple | Jake / Theo | Planned
| SF-Team | Team short-form | Team voices on individual cadences (Sean, Josh, Matej, others) | All 5 pillars | Barbora (coord) | Planned
TBD 2026
| C1 | Case study | Swiftly | Elite Engineering Talent | Kuba (pending) | In production
| C3 | Case study | Nasdaq Private Market (or anonymized) | Deep Domain Expertise | DMT (rotating) | Permissions pending

## By Pillar
Coverage by pillar — what's mapped to each of the 5
ID | Type | Title | Owner | Target month | Status
AI-Native Delivery · 10 pieces · owner: Andy
R1 | Industry report | AI-Native Delivery: A 2026 Playbook for Engineering Leaders | Andy | Aug 2026 | Committed
R3 | Industry report | What CTOs Are Building in 2027: A Tech Stack Survey | Andy | Late Nov 2026 | Committed
D4 | Gated downloadable | The AI-Native Engineering Team: A CTO's Operating Playbook | Andy | Q4 2026 | Idea
T4 | TL article | Production AI Patterns: RAG (Series 1 of 2) | Andy | Jul 2026 | Committed
T5 | TL article | Why CTOs Get the AI Question Wrong | Andy | Aug 2026 | Committed
T7 | TL article | Production AI Patterns: Eval Loops (Series 2 of 2) | Andy | Sep 2026 | Committed
T11 | TL article | Inside Our AI Delivery Process: How an AI-Native Team Actually Ships | Andy | Nov 2026 | Committed
W6 | Services page | AI Native Development (new) | Andy | Aug 2026 | To start
W8 | Services page | Agentic AI Systems (refresh) | Andy | Q3–Q4 2026 | To start
W11 | Situations page (SEO) | Integrating AI into your product | Andy | Q4 2026 / Q1 2027 | To start
Product Thinking · 5 pieces · owner: Denisa
D3 | Gated downloadable | The Roadmap Reality Check: A CPO's Field Guide | Denisa | Q3–Q4 2026 | Idea
T2 | TL article | Why "More Engineers" Is Almost Never the Answer | Denisa | Jun 2026 | Committed
T6 | TL article | The Product Roadmap Test: 5 Questions Every CPO Should Ask Before Approving Next Sprint | Denisa | Aug 2026 | Committed
W7 | Services page | Design & Discovery (refresh) | Denisa | Q3–Q4 2026 | To start
W12 | Situations page (SEO) | Strengthening your product org | Denisa | Q4 2026 / Q1 2027 | To start
Deep Domain Expertise · 10 pieces · owner: DMT (rotating)
R2 | Industry report | Engineering in Healthcare: A Practitioner's Playbook for 2026 (working title) | DMT (rotating) | Oct 2026 | Committed
T10 | TL article | Compliance-by-Design: Avoiding the Late-Stage Rewrite | DMT (rotating) | Oct 2026 | Committed
C2 | Case study | OpenLoop Health (or anonymized) | DMT (rotating) | Jun 2026 | In Webflow
C3 | Case study | Nasdaq Private Market (or anonymized) | DMT (rotating) | TBD 2026 | Permissions pending
C4 | Case study | Exam Papers Plus | DMT (rotating) | Q3 2026 | To start
C5 | Case study | Learning Spring | DMT (rotating) | Q3 2026 | To start
W1 | Industry page | Education industry page (new) | DMT (rotating) | Q3 2026 | To start
W2 | Industry page | Finance industry page (rename from Fintech) | DMT (rotating) | Q3 2026 | In flight
W3 | Industry page | Healthcare industry page (rename from Healthtech) | DMT (rotating) | Q3 2026 | In flight
W4 | Industry page | Cybersecurity industry page | DMT (rotating) | Q3–Q4 2026 | To start
Elite Engineering Talent · 6 pieces · owner: Kuba (pending)
D1 | Gated downloadable | SaaS Scaling Guide v4 | Kuba (pending) | Jun 2026 | In design
T3 | TL article | Inside the OAK'S LAB Way: How Senior Engineers Ramp in Week One | Kuba (pending) | Jul 2026 | Committed
T9 | TL article | AI Code Review: What's Actually Working in Production | Kuba (pending) | Oct 2026 | Committed
T12 | TL article | Compliance Across Verticals: A CTO's Operating Framework | Kuba (pending) | Dec 2026 | Committed
C1 | Case study | Swiftly | Kuba (pending) | TBD 2026 | In production
W10 | Situations page (SEO) | Scaling an existing product | Kuba (pending) | Q4 2026 / Q1 2027 | To start
Outsourcing · 5 pieces · owner: Jake
D2 | Gated downloadable | Choosing a Dev Partner: A CTO's Buyer's Guide | Jake | Q3–Q4 2026 | Idea
T1 | TL article | Choosing Your Outsourcing Partner: A CTO's Decision Framework | Jake | Jun 2026 | Committed
T8 | TL article | The Real Cost of a 12-Month Engineering Push: Hire vs Partner | Jake | Sep 2026 | Committed
W9 | Situations page (SEO) | Launching a new product | Jake | Q4 2026 / Q1 2027 | To start
W13 | Situations page (SEO) | Establishing your European engineering hub | Jake | Q4 2026 / Q1 2027 | To start
Product Thinking + Elite Engineering Talent · 1 piece · owner: Denisa + Kuba (pending)
W5 | Industry page | SaaS industry page | Denisa + Kuba (pending) | Q3–Q4 2026 | To start
All 5 pillars · 7 pieces · owner: Barbora (coord)
K1 | KH backlog | June batch (20/120 cumulative) | Barbora (coord) | Jun 2026 | Committed
K2 | KH backlog | July batch (40/120 cumulative) | Barbora (coord) | Jul 2026 | Committed
K3 | KH backlog | August batch (60/120 cumulative) | Barbora (coord) | Aug 2026 | Committed
K4 | KH backlog | September batch (80/120 cumulative) | Barbora (coord) | Sep 2026 | Committed
K5 | KH backlog | October batch (100/120 cumulative) | Barbora (coord) | Oct 2026 | Committed
K6 | KH backlog | Nov–Dec maintenance | Barbora (coord) | Nov–Dec 2026 | Committed
SF-Team | Team short-form | Team voices on individual cadences (Sean, Josh, Matej, others) | Barbora (coord) | Jun–Dec 2026 | Planned
Multi-pillar (cross-cuts all) · 2 pieces · owner: Barbora (coord)
E1 | Email nurture flow | Flow A — Website downloads (5 emails over 4 weeks) | Barbora (coord) | Aug 2026 launch | To start
E2 | Email nurture flow | Flow B — LinkedIn Lead Gen (4 emails over 4 weeks) | Barbora (coord) | Sprint 11–12 (accelerated) | To start
Multiple · 8 pieces · owner: Jake / Theo
SF-Jun-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Jun 2026 | Planned
SF-Jul-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Jul 2026 | Planned
SF-Aug-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Aug 2026 | Planned
SF-Sep-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Sep 2026 | Planned
SF-Oct-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Oct 2026 | Planned
SF-Nov-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Nov 2026 | Planned
SF-Dec-J | Standalone short-form | Jake standalone LinkedIn posts (~4–6) | Jake / Theo | Dec 2026 | Planned
SF-H2-T | Standalone short-form (Theo) | Theo occasional LinkedIn posts (~7–14 across H2) | Jake / Theo | Jun–Dec 2026 | Planned
— · 3 pieces · owner: Barbora
N1 | Newsletter | July newsletter (+ AI Roundup section) | Barbora | Jul 2026 | Committed
N2 | Newsletter | October newsletter (+ AI Roundup section) | Barbora | Oct 2026 | Committed
N3 | Newsletter | December newsletter (year-end + AI Roundup) | Barbora | Dec 2026 | Committed

## By Content Type
Coverage by content type
ID | Title | Pillar | Owner | Target month | Status
Industry report · 3 pieces
R1 | AI-Native Delivery: A 2026 Playbook for Engineering Leaders | AI-Native Delivery | Andy | Aug 2026 | Committed
R2 | Engineering in Healthcare: A Practitioner's Playbook for 2026 (working title) | Deep Domain Expertise | DMT (rotating) | Oct 2026 | Committed
R3 | What CTOs Are Building in 2027: A Tech Stack Survey | AI-Native Delivery | Andy | Late Nov 2026 | Committed
Gated downloadable · 4 pieces
D1 | SaaS Scaling Guide v4 | Elite Engineering Talent | Kuba (pending) | Jun 2026 | In design
D2 | Choosing a Dev Partner: A CTO's Buyer's Guide | Outsourcing | Jake | Q3–Q4 2026 | Idea
D3 | The Roadmap Reality Check: A CPO's Field Guide | Product Thinking | Denisa | Q3–Q4 2026 | Idea
D4 | The AI-Native Engineering Team: A CTO's Operating Playbook | AI-Native Delivery | Andy | Q4 2026 | Idea
TL article · 12 pieces
T1 | Choosing Your Outsourcing Partner: A CTO's Decision Framework | Outsourcing | Jake | Jun 2026 | Committed
T2 | Why "More Engineers" Is Almost Never the Answer | Product Thinking | Denisa | Jun 2026 | Committed
T3 | Inside the OAK'S LAB Way: How Senior Engineers Ramp in Week One | Elite Engineering Talent | Kuba (pending) | Jul 2026 | Committed
T4 | Production AI Patterns: RAG (Series 1 of 2) | AI-Native Delivery | Andy | Jul 2026 | Committed
T5 | Why CTOs Get the AI Question Wrong | AI-Native Delivery | Andy | Aug 2026 | Committed
T6 | The Product Roadmap Test: 5 Questions Every CPO Should Ask Before Approving Next Sprint | Product Thinking | Denisa | Aug 2026 | Committed
T7 | Production AI Patterns: Eval Loops (Series 2 of 2) | AI-Native Delivery | Andy | Sep 2026 | Committed
T8 | The Real Cost of a 12-Month Engineering Push: Hire vs Partner | Outsourcing | Jake | Sep 2026 | Committed
T9 | AI Code Review: What's Actually Working in Production | Elite Engineering Talent | Kuba (pending) | Oct 2026 | Committed
T10 | Compliance-by-Design: Avoiding the Late-Stage Rewrite | Deep Domain Expertise | DMT (rotating) | Oct 2026 | Committed
T11 | Inside Our AI Delivery Process: How an AI-Native Team Actually Ships | AI-Native Delivery | Andy | Nov 2026 | Committed
T12 | Compliance Across Verticals: A CTO's Operating Framework | Elite Engineering Talent | Kuba (pending) | Dec 2026 | Committed
Case study · 5 pieces
C1 | Swiftly | Elite Engineering Talent | Kuba (pending) | TBD 2026 | In production
C2 | OpenLoop Health (or anonymized) | Deep Domain Expertise | DMT (rotating) | Jun 2026 | In Webflow
C3 | Nasdaq Private Market (or anonymized) | Deep Domain Expertise | DMT (rotating) | TBD 2026 | Permissions pending
C4 | Exam Papers Plus | Deep Domain Expertise | DMT (rotating) | Q3 2026 | To start
C5 | Learning Spring | Deep Domain Expertise | DMT (rotating) | Q3 2026 | To start
Industry page · 5 pieces
W1 | Education industry page (new) | Deep Domain Expertise | DMT (rotating) | Q3 2026 | To start
W2 | Finance industry page (rename from Fintech) | Deep Domain Expertise | DMT (rotating) | Q3 2026 | In flight
W3 | Healthcare industry page (rename from Healthtech) | Deep Domain Expertise | DMT (rotating) | Q3 2026 | In flight
W4 | Cybersecurity industry page | Deep Domain Expertise | DMT (rotating) | Q3–Q4 2026 | To start
W5 | SaaS industry page | Product Thinking + Elite Engineering Talent | Denisa + Kuba (pending) | Q3–Q4 2026 | To start
Services page · 3 pieces
W6 | AI Native Development (new) | AI-Native Delivery | Andy | Aug 2026 | To start
W7 | Design & Discovery (refresh) | Product Thinking | Denisa | Q3–Q4 2026 | To start
W8 | Agentic AI Systems (refresh) | AI-Native Delivery | Andy | Q3–Q4 2026 | To start
Situations page (SEO) · 5 pieces
W9 | Launching a new product | Outsourcing | Jake | Q4 2026 / Q1 2027 | To start
W10 | Scaling an existing product | Elite Engineering Talent | Kuba (pending) | Q4 2026 / Q1 2027 | To start
W11 | Integrating AI into your product | AI-Native Delivery | Andy | Q4 2026 / Q1 2027 | To start
W12 | Strengthening your product org | Product Thinking | Denisa | Q4 2026 / Q1 2027 | To start
W13 | Establishing your European engineering hub | Outsourcing | Jake | Q4 2026 / Q1 2027 | To start
Newsletter · 3 pieces
N1 | July newsletter (+ AI Roundup section) | — | Barbora | Jul 2026 | Committed
N2 | October newsletter (+ AI Roundup section) | — | Barbora | Oct 2026 | Committed
N3 | December newsletter (year-end + AI Roundup) | — | Barbora | Dec 2026 | Committed
Email nurture flow · 2 pieces
E1 | Flow A — Website downloads (5 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | Aug 2026 launch | To start
E2 | Flow B — LinkedIn Lead Gen (4 emails over 4 weeks) | Multi-pillar (cross-cuts all) | Barbora (coord) | Sprint 11–12 (accelerated) | To start
KH backlog · 6 pieces
K1 | June batch (20/120 cumulative) | All 5 pillars | Barbora (coord) | Jun 2026 | Committed
K2 | July batch (40/120 cumulative) | All 5 pillars | Barbora (coord) | Jul 2026 | Committed
K3 | August batch (60/120 cumulative) | All 5 pillars | Barbora (coord) | Aug 2026 | Committed
K4 | September batch (80/120 cumulative) | All 5 pillars | Barbora (coord) | Sep 2026 | Committed
K5 | October batch (100/120 cumulative) | All 5 pillars | Barbora (coord) | Oct 2026 | Committed
K6 | Nov–Dec maintenance | All 5 pillars | Barbora (coord) | Nov–Dec 2026 | Committed
Standalone short-form · 7 pieces
SF-Jun-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jun 2026 | Planned
SF-Jul-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Jul 2026 | Planned
SF-Aug-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Aug 2026 | Planned
SF-Sep-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Sep 2026 | Planned
SF-Oct-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Oct 2026 | Planned
SF-Nov-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Nov 2026 | Planned
SF-Dec-J | Jake standalone LinkedIn posts (~4–6) | Multiple | Jake / Theo | Dec 2026 | Planned
Standalone short-form (Theo) · 1 piece
SF-H2-T | Theo occasional LinkedIn posts (~7–14 across H2) | Multiple | Jake / Theo | Jun–Dec 2026 | Planned
Team short-form · 1 piece
SF-Team | Team voices on individual cadences (Sean, Josh, Matej, others) | All 5 pillars | Barbora (coord) | Jun–Dec 2026 | Planned

## Legend
How to use this calendar
Pillars + owners
AI-Native Delivery | Owner: Andy
Product Thinking | Owner: Denisa
Deep Domain Expertise | Owner: DMT (rotating)
Elite Engineering Talent | Owner: Kuba (pending)
Outsourcing | Owner: Jake
Status colors
Committed
In design
In production
In flight
In Webflow
Planned
Idea
To start
Permissions pending
Conventions
Editorial principle — AI | Distinguish AI delivery (how OAK'S LAB builds — R1, R3, W6, T11, D4) from AI as product feature (what clients build — W8, client AI case studies). Every AI piece must signal which half in title + first paragraph.
Writing convention | Nur drafts all long-form. Byline = published author; Drafted by = first-draft writer. DMT, product, and engineering experts review, give input, lend byline. For technical pieces Nur interviews the SME first.
Short-form posts | Jake monthly standalone rows (SF-Jun-J through SF-Dec-J) — ~4–6 posts/mo, opportunistic, CTO challenges + founder voice, Jake writes self with light Barbora support. SF-H2-T = Theo's ~7–14 posts across H2 (~1–2/mo). SF-Team = other voices (Sean highest at 2–3/wk, Josh 1/wk, Matej ~weekly, Denisa/Andy occasional). Total ~30–50 by December. Jake's cadence IS the TLA pipeline.
Industry reports (R1–R3) | R1 AI-Native Delivery (Aug), R2 Healthcare (Oct), R3 What CTOs Are Building in 2027 — tech-stack survey (late Nov). Each unlocks 4–6 weeks of derivatives.
Downloadables (D1–D4) | D1 SaaS Scaling Guide v4 (launching now as LinkedIn Lead Gen). D2 CTO's Buyer's Guide (Outsourcing). D3 Roadmap Reality Check (Product Thinking, CPO-targeted). D4 AI-Native Engineering Team Playbook (replaces 20-to-200 scaling).
TL articles (T1–T12) | Twelve long-form Jun–Dec, ~1,500 words, ungated. T1, T6, T11, T12 changed since first draft — see Notes. Audience CTO-primary.
Newsletters (N1–N3) | Three quarterly. Each now includes 'AI Roundup' (replaces separate LinkedIn AI newsletter idea).
Email nurture flows (E1, E2) | Flow A triggered by website downloads. Flow B triggered by LinkedIn Lead Gen — accelerated to Sprint 11–12.
Source piece | When a piece is a derivative or companion, the parent ID is in the Source column.